## Project_Overview
Project | ISO 27001 Compliance Gap Assessment & Risk Register Dashboard
Simulated Organization | Northstar Digital Services Pvt. Ltd.
Assessment Date | 2026-07-10
Purpose | Demonstrate a practical GRC workflow for assessing selected ISO/IEC 27001:2022 Annex A controls, documenting gaps, evaluating risks and tracking remediation.
Assessment Scope | 40 representative controls across Organizational, People, Physical and Technological themes.
Assessment Type | Portfolio simulation; not a certification audit, conformity assessment or statement of ISO certification.
Risk Methodology | Inherent Risk Score = Likelihood × Impact, using a 1–5 scale. Risk bands are defined in the Lookup_Lists sheet.
Evidence Principle | Assessment results are based on simulated evidence references created for this portfolio project.
Build Status | Excel phase complete. Power BI dashboard is the next phase.
Workbook Flow | Control_Master → Gap_Assessment → Risk_Register → Remediation_Tracker → Power BI

## Management_Summary
Metric | Value | Definition
Total Controls | 40 | Finalized representative control universe assessed.
Implemented Controls | 18 | Controls assessed as fully implemented.
Partially Implemented Controls | 20 | Controls with evidence but material improvement needed.
Not Implemented Controls | 2 | Controls without an established implementation.
Not Applicable Controls | 0 | Controls determined not applicable; none used in this simulation.
Overall Compliance Score | 70% | Weighted portfolio score: Implemented = 100%, Partial = 50%, Not Implemented = 0%.
Total Risks | 13 | Risks entered into the risk register from significant gaps.
Critical Risks | 6 | Risks with inherent score 17–25.
High Risks | 7 | Risks with inherent score 10–16.
Medium Risks | 0 | Risks with inherent score 5–9.
Low Risks | 0 | Risks with inherent score 1–4.
Open Remediation Actions | 1048575 | Actions not yet completed or accepted.
Average Remediation Completion | 15.38% | Average completion percentage across remediation actions.

## Control_Master
Control_ID | Control_Category | Control_Name | Control_Objective | Assessment_Criteria | Evidence_Required | Applicable
A.5.1 | Organizational | Policies for information security | Establish, approve, communicate and periodically review information security policies. | Verify approved policy documents, version history, review evidence and communication records. | Approved information security policy; review record; communication evidence | Yes
A.5.2 | Organizational | Information security roles and responsibilities | Define and assign information security responsibilities and accountability. | Check role descriptions, RACI/assignment records and management approvals. | RACI matrix; job descriptions; responsibility assignments | Yes
A.5.4 | Organizational | Management responsibilities | Ensure management establishes and supports information security responsibilities and practices. | Verify management directives, approvals, reviews and evidence of security responsibilities. | Management approvals; meeting minutes; directives | Yes
A.5.7 | Organizational | Threat intelligence | Collect and use relevant threat information to support information security decisions. | Check whether threat information is sourced, reviewed and used in risk or security decisions. | Threat reports; intelligence subscriptions; review records | Yes
A.5.9 | Organizational | Inventory of information and other associated assets | Maintain an appropriate inventory of information and associated assets. | Verify asset inventory completeness, ownership, classification and review frequency. | Asset register; ownership records; review evidence | Yes
A.5.10 | Organizational | Acceptable use of information and other associated assets | Define acceptable use and handling expectations for organizational information and assets. | Check approved acceptable-use requirements and evidence that users acknowledge them. | Acceptable-use policy; acknowledgements; training records | Yes
A.5.12 | Organizational | Classification of information | Classify information according to organizational security needs. | Verify classification scheme, assigned classifications and handling rules. | Classification policy; sample classified records; handling rules | Yes
A.5.14 | Organizational | Information transfer | Protect information during transfer using defined requirements and approved methods. | Check transfer procedures, approved channels and safeguards for sensitive information. | Transfer procedure; secure-transfer configuration; agreements | Yes
A.5.15 | Organizational | Access control | Establish rules governing logical and physical access to information and associated assets. | Verify access-control policy, authorization rules and periodic review mechanisms. | Access-control policy; authorization records; review reports | Yes
A.5.16 | Organizational | Identity management | Manage identities throughout their lifecycle. | Check joiner/mover/leaver processes, unique identities and lifecycle controls. | Identity lifecycle procedure; IAM records; termination samples | Yes
A.5.17 | Organizational | Authentication information | Protect authentication information through defined management and handling practices. | Verify password/authentication requirements and secure handling procedures. | Authentication policy; configuration evidence; procedures | Yes
A.5.18 | Organizational | Access rights | Provision, review, modify and remove access rights according to business need. | Sample access requests, approvals, periodic reviews and removals. | Access requests; approval records; access review reports | Yes
A.5.19 | Organizational | Information security in supplier relationships | Address information security risks associated with supplier relationships. | Check supplier security requirements, due diligence and contractual controls. | Supplier security assessment; contracts; due-diligence records | Yes
A.5.20 | Organizational | Addressing information security within supplier agreements | Define relevant information security requirements in supplier agreements. | Review representative supplier contracts for security clauses and responsibilities. | Supplier agreements; security clauses; contract checklist | Yes
A.5.23 | Organizational | Information security for use of cloud services | Manage information security risks associated with acquisition, use and exit from cloud services. | Verify cloud security requirements, provider assessment, configuration responsibilities and exit planning. | Cloud assessment; contracts; configuration baseline; exit plan | Yes
A.5.24 | Organizational | Information security incident management planning and preparation | Establish capabilities and responsibilities for preparing to manage information security incidents. | Check incident response plan, roles, escalation paths and readiness exercises. | Incident response plan; contact list; exercise records | Yes
A.5.25 | Organizational | Assessment and decision on information security events | Assess information security events and determine whether they constitute incidents. | Verify triage criteria, severity classification and escalation decisions. | Incident triage procedure; sample tickets; severity matrix | Yes
A.5.26 | Organizational | Response to information security incidents | Respond to information security incidents using defined procedures. | Review incident records for containment, eradication, recovery and communications. | Incident tickets; response playbooks; post-incident records | Yes
A.5.27 | Organizational | Learning from information security incidents | Use incident outcomes to improve information security. | Check root-cause analysis, lessons learned and resulting corrective actions. | Post-incident reviews; RCA; corrective-action records | Yes
A.5.30 | Organizational | ICT readiness for business continuity | Prepare ICT capabilities to support business continuity requirements. | Verify continuity requirements, recovery arrangements, testing and documented dependencies. | BC/DR plan; RTO/RPO records; test results | Yes
A.5.31 | Organizational | Legal, statutory, regulatory and contractual requirements | Identify and maintain applicable information security obligations. | Check legal/regulatory register, contractual obligations and review process. | Compliance obligations register; contracts; legal review records | Yes
A.5.34 | Organizational | Privacy and protection of PII | Identify and manage privacy and personally identifiable information protection requirements. | Verify PII inventory, privacy requirements, handling procedures and accountability. | PII inventory; privacy policy; processing records | Yes
A.5.35 | Organizational | Independent review of information security | Conduct independent reviews of information security management and controls. | Check review plan, independence, findings and follow-up actions. | Audit/review reports; review plan; action tracker | Yes
A.5.36 | Organizational | Compliance with policies, rules and standards for information security | Regularly review compliance with internal information security requirements. | Verify compliance checks, findings, exceptions and remediation tracking. | Compliance checklists; findings; remediation records | Yes
A.6.1 | People | Screening | Perform appropriate personnel screening before and, where applicable, during employment. | Verify screening criteria, completion records and role-based requirements. | Screening procedure; sample verification records | Yes
A.6.3 | People | Information security awareness, education and training | Provide appropriate security awareness, education and training. | Check training content, completion rates, frequency and role-specific training. | Training materials; attendance/completion reports | Yes
A.6.5 | People | Responsibilities after termination or change of employment | Manage security responsibilities after termination or role change. | Sample offboarding/role-change records for access removal and continuing obligations. | Offboarding checklist; access removal records; agreements | Yes
A.6.7 | People | Remote working | Protect information accessed or processed during remote working. | Verify remote-working requirements, endpoint safeguards and secure connectivity. | Remote-work policy; VPN/endpoint evidence; user acknowledgements | Yes
A.7.1 | Physical | Physical security perimeters | Define and protect physical security boundaries for relevant facilities. | Inspect perimeter controls, access boundaries and documented physical-security requirements. | Physical security policy; site controls; inspection records | Yes
A.7.2 | Physical | Physical entry | Control physical access to secure areas. | Verify badges, visitor controls, access logs and authorization procedures. | Access logs; visitor register; badge records | Yes
A.7.4 | Physical | Physical security monitoring | Monitor relevant premises for unauthorized physical access. | Check CCTV/alarm coverage, monitoring responsibilities and retention arrangements. | CCTV/alarm records; monitoring procedure; retention settings | Yes
A.7.7 | Physical | Clear desk and clear screen | Reduce exposure of sensitive information through clear-desk and clear-screen practices. | Check policy, user guidance and evidence of periodic compliance checks where applicable. | Clear-desk policy; awareness records; inspection checklist | Yes
A.7.10 | Physical | Storage media | Manage storage media through acquisition, use, transport and disposal. | Verify media handling, labeling, transport and secure disposal practices. | Media register; disposal certificates; handling procedure | Yes
A.8.2 | Technological | Privileged access rights | Restrict and manage privileged access according to business need. | Review privileged accounts, approvals, MFA, monitoring and periodic recertification. | Privileged account list; approvals; access reviews | Yes
A.8.5 | Technological | Secure authentication | Implement secure authentication mechanisms appropriate to access risk. | Check MFA, password policy, authentication configuration and exception handling. | IAM configuration; MFA reports; authentication policy | Yes
A.8.7 | Technological | Protection against malware | Protect systems against malware using preventive and detective measures. | Verify endpoint protection coverage, update status, alerts and response procedures. | EDR/antimalware console; coverage report; alert samples | Yes
A.8.8 | Technological | Management of technical vulnerabilities | Identify, evaluate and address technical vulnerabilities. | Check vulnerability scanning, severity assessment, remediation SLAs and exceptions. | Vulnerability reports; remediation tickets; exception records | Yes
A.8.13 | Technological | Information backup | Maintain backups appropriate to business and information security requirements. | Verify backup scope, frequency, protection, retention and restoration testing. | Backup reports; retention settings; restore-test evidence | Yes
A.8.15 | Technological | Logging | Generate and protect logs needed for security and operational monitoring. | Check logging coverage, retention, protection and review responsibilities. | Log configuration; retention settings; review records | Yes
A.8.16 | Technological | Monitoring activities | Monitor systems and networks for relevant anomalies and security events. | Verify monitoring coverage, alert handling, escalation and review. | SIEM/monitoring reports; alert tickets; escalation records | Yes

## Gap_Assessment
Assessment_ID | Control_ID | Control_Category | Control_Name | Assessment_Date | Status | Maturity | Evidence_Available | Evidence_Reference | Gap_Description | Assessor_Notes | Gap_Owner | Priority
GA-001 | A.5.1 | Organizational | Policies for information security | 2026-07-10 | Implemented | Defined / Operating | Yes | ISMS-POL-001 v2.1 |  | Policy approved by management and reviewed in June 2026. | Information Security | Low
GA-002 | A.5.2 | Organizational | Information security roles and responsibilities | 2026-07-10 | Implemented | Defined / Operating | Yes | ISMS-RACI-001 |  | Security roles are assigned across IT, HR, Legal and management. | Information Security | Low
GA-003 | A.5.4 | Organizational | Management responsibilities | 2026-07-10 | Implemented | Defined / Operating | Yes | MGMT-MIN-014 |  | Management reviews security responsibilities during quarterly governance meetings. | Information Security | Low
GA-004 | A.5.7 | Organizational | Threat intelligence | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | TI-LOG-003 | Formalize threat intelligence sources, review cadence and decision records. | Threat feeds are reviewed by IT, but there is no documented recurring threat-intelligence review process. | Information Security | Medium
GA-005 | A.5.9 | Organizational | Inventory of information and other associated assets | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | ASSET-REG-2026Q2 | Expand asset inventory and establish quarterly ownership review. | Hardware is inventoried, but SaaS and information assets are not consistently mapped to owners. | Information Security | Medium
GA-006 | A.5.10 | Organizational | Acceptable use of information and other associated assets | 2026-07-10 | Implemented | Defined / Operating | Yes | AUP-001 v2.0 |  | Acceptable-use policy is approved and acknowledged by employees. | Information Security | Low
GA-007 | A.5.12 | Organizational | Classification of information | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | INFO-CLASS-001 | Improve labeling guidance and perform periodic compliance checks. | Classification levels exist, but sampled documents were inconsistently labeled. | Information Security | Medium
GA-008 | A.5.14 | Organizational | Information transfer | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | TRN-STD-002 | Standardize secure-transfer requirements in supplier workflows. | Approved transfer methods exist, but supplier transfer requirements are not consistently documented. | Information Security | Medium
GA-009 | A.5.15 | Organizational | Access control | 2026-07-10 | Implemented | Defined / Operating | Yes | ACC-POL-001 |  | Access control policy and authorization principles are established. | Information Security | Low
GA-010 | A.5.16 | Organizational | Identity management | 2026-07-10 | Implemented | Defined / Operating | Yes | IAM-SOP-004 |  | Joiner/mover/leaver workflow is integrated with HR tickets. | Information Security | Low
GA-011 | A.5.17 | Organizational | Authentication information | 2026-07-10 | Implemented | Defined / Operating | Yes | AUTH-POL-002 |  | Authentication requirements and credential handling procedures are documented. | Information Security | Low
GA-012 | A.5.18 | Organizational | Access rights | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | ACC-REV-2026Q2 | Complete quarterly access certification for all critical applications. | Access requests are approved, but quarterly recertification coverage is incomplete. | Information Security | High
GA-013 | A.5.19 | Organizational | Information security in supplier relationships | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | SUP-SEC-REG-001 | Extend risk-based supplier assessment coverage. | Supplier security due diligence exists for critical vendors but not consistently for medium-risk suppliers. | Information Security | Medium
GA-014 | A.5.20 | Organizational | Addressing information security within supplier agreements | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | SUP-CON-CHK-001 | Refresh legacy agreements using approved security clause checklist. | Security clauses are included in major supplier contracts; legacy contracts are not consistently updated. | Information Security | Medium
GA-015 | A.5.23 | Organizational | Information security for use of cloud services | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | CLOUD-ASSMT-002 | Document cloud exit strategy and shared-responsibility ownership. | Cloud providers are assessed, but formal exit plans and configuration ownership are inconsistent. | Information Security | Medium
GA-016 | A.5.24 | Organizational | Information security incident management planning and preparation | 2026-07-10 | Implemented | Defined / Operating | Yes | IR-PLAN-001 v3.0 |  | Incident response plan includes roles, escalation and communications. | Information Security | Low
GA-017 | A.5.25 | Organizational | Assessment and decision on information security events | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | IR-TRIAGE-001 | Implement mandatory severity classification field. | Events are triaged, but severity criteria are not consistently recorded in tickets. | Information Security | Medium
GA-018 | A.5.26 | Organizational | Response to information security incidents | 2026-07-10 | Implemented | Defined / Operating | Yes | IR-REC-2026-04 |  | Recent incident records demonstrate containment and recovery steps. | Information Security | Low
GA-019 | A.5.27 | Organizational | Learning from information security incidents | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | IR-RCA-LOG-001 | Standardize post-incident review criteria. | Lessons learned are captured for major incidents but not consistently for low-severity incidents. | Information Security | Medium
GA-020 | A.5.30 | Organizational | ICT readiness for business continuity | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | BCP-ICT-001 | Expand continuity test scope to critical application dependencies. | Backups and recovery arrangements exist, but not all critical application dependencies are included in continuity testing. | Information Security | Medium
GA-021 | A.5.31 | Organizational | Legal, statutory, regulatory and contractual requirements | 2026-07-10 | Implemented | Defined / Operating | Yes | LEGAL-REG-001 |  | Applicable legal and contractual obligations are recorded and reviewed. | Information Security | Low
GA-022 | A.5.34 | Organizational | Privacy and protection of PII | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | PRIV-REG-001 | Complete PII inventory and ownership mapping. | PII processing is documented for major systems, but the inventory is incomplete for several SaaS tools. | Information Security | High
GA-023 | A.5.35 | Organizational | Independent review of information security | 2026-07-10 | Not Implemented | Not Established | No | AUD-PLAN-001 | Schedule an independent ISMS/security review and track findings. | No independent information security review has been completed during the assessment period. | Information Security | Critical
GA-024 | A.5.36 | Organizational | Compliance with policies, rules and standards for information security | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | COMP-CHECK-2026Q2 | Standardize compliance evidence retention and exception tracking. | Internal compliance checks are performed, but evidence retention is inconsistent. | Information Security | Medium
GA-025 | A.6.1 | People | Screening | 2026-07-10 | Implemented | Defined / Operating | Yes | HR-SCR-001 |  | Pre-employment screening is performed according to role requirements. | HR / Information Security | Low
GA-026 | A.6.3 | People | Information security awareness, education and training | 2026-07-10 | Implemented | Defined / Operating | Yes | SEC-TRAIN-2026 |  | Annual awareness training reached 96% completion; remaining users are tracked. | HR / Information Security | Low
GA-027 | A.6.5 | People | Responsibilities after termination or change of employment | 2026-07-10 | Implemented | Defined / Operating | Yes | HR-OFF-001 |  | Termination workflow includes access removal and continuing obligations. | HR / Information Security | Low
GA-028 | A.6.7 | People | Remote working | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | REMOTE-SEC-001 | Extend endpoint compliance monitoring to contractor devices. | Remote work requirements exist, but endpoint compliance reporting is incomplete for contractors. | HR / Information Security | Medium
GA-029 | A.7.1 | Physical | Physical security perimeters | 2026-07-10 | Implemented | Defined / Operating | Yes | PHY-SEC-001 |  | Office perimeter controls and restricted-area boundaries are documented. | Facilities / Security | Low
GA-030 | A.7.2 | Physical | Physical entry | 2026-07-10 | Implemented | Defined / Operating | Yes | PHY-ACC-LOG-2026 |  | Badge access and visitor registration are in use. | Facilities / Security | Low
GA-031 | A.7.4 | Physical | Physical security monitoring | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | CCTV-LOG-001 | Document retention verification and periodic monitoring checks. | CCTV covers critical areas, but retention verification is not consistently documented. | Facilities / Security | Medium
GA-032 | A.7.7 | Physical | Clear desk and clear screen | 2026-07-10 | Implemented | Defined / Operating | Yes | CDCS-POL-001 |  | Clear desk and clear screen requirements are communicated to staff. | Facilities / Security | Low
GA-033 | A.7.10 | Physical | Storage media | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | MEDIA-REG-001 | Complete media inventory and disposal evidence reconciliation. | Media disposal is controlled, but older removable media records are incomplete. | Facilities / Security | Medium
GA-034 | A.8.2 | Technological | Privileged access rights | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | PAM-REG-001 | Complete privileged access recertification and exception review. | Privileged accounts are inventoried, but quarterly recertification is incomplete. | IT Security | High
GA-035 | A.8.5 | Technological | Secure authentication | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | MFA-REPORT-2026Q2 | Extend MFA coverage to remaining legacy applications. | MFA is enabled for major cloud services but not yet universal for legacy internal applications. | IT Security | High
GA-036 | A.8.7 | Technological | Protection against malware | 2026-07-10 | Implemented | Defined / Operating | Yes | EDR-COV-2026Q2 |  | Endpoint protection coverage is 99% with centralized alerting. | IT Security | Low
GA-037 | A.8.8 | Technological | Management of technical vulnerabilities | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | VULN-SCAN-2026Q2 | Strengthen remediation tracking and escalation for overdue vulnerabilities. | Monthly scanning occurs, but some high-severity findings exceed remediation SLA. | IT Security | High
GA-038 | A.8.13 | Technological | Information backup | 2026-07-10 | Implemented | Defined / Operating | Yes | BKP-REP-2026Q2 |  | Critical systems are backed up and restore tests are performed. | IT Security | Low
GA-039 | A.8.15 | Technological | Logging | 2026-07-10 | Partially Implemented | Defined / Partially Operating | Partial | LOG-STD-001 | Standardize retention requirements and coverage. | Central logging exists for key systems, but log retention is inconsistent across legacy applications. | IT Security | Medium
GA-040 | A.8.16 | Technological | Monitoring activities | 2026-07-10 | Not Implemented | Not Established | No | MON-001 | Implement centralized monitoring and alert escalation for critical systems. | No formal centralized monitoring capability is currently in place for several critical systems. | IT Security | Critical

## Risk_Register
Risk_ID | Assessment_ID | Risk_Title | Risk_Description | Asset | Threat | Vulnerability | Likelihood | Impact | Inherent_Risk_Score | Inherent_Risk_Level | Risk_Owner | Treatment | Mitigation_Action | Target_Date | Status | Residual_Likelihood | Residual_Impact | Residual_Risk_Score | Residual_Risk_Level
R-001 | GA-004 | Inadequate threat intelligence process | Security decisions may not consistently incorporate current threat information. | Security decision process | Insufficient documented threat-intelligence review | Threat intelligence not formally reviewed on a recurring basis | 3 | 4 | 12 | High | IT Security | Mitigate | Formalize threat intelligence sources, review cadence and decision records | 2026-09-30 | Open | 2 | 3 | 6 | Medium
R-002 | GA-005 | Incomplete asset inventory | Untracked SaaS or information assets may remain outside security controls. | Information assets / SaaS | Incomplete ownership mapping | SaaS and information assets are not consistently mapped to owners | 4 | 4 | 16 | High | IT Operations | Mitigate | Complete asset discovery and quarterly ownership certification | 2026-09-20 | Open | 3 | 3 | 9 | Medium
R-003 | GA-007 | Inconsistent information classification | Sensitive information may receive insufficient handling protection. | Business information | Inconsistent labeling | Sampled information was not consistently labeled | 3 | 4 | 12 | High | Information Security | Mitigate | Reinforce classification guidance and conduct periodic checks | 2026-09-25 | Open | 2 | 3 | 6 | Medium
R-004 | GA-012 | Incomplete access recertification | Excess or stale access may remain active longer than necessary. | Critical applications | Incomplete periodic review | Quarterly access recertification does not cover all critical applications | 4 | 5 | 20 | Critical | IT Security | Mitigate | Complete quarterly access certification for critical applications | 2026-09-15 | In Progress | 3 | 4 | 12 | High
R-005 | GA-015 | Weak cloud exit planning | The organization may face security and continuity issues when terminating a cloud service. | Cloud services | Incomplete exit planning | Formal cloud exit plans are inconsistent | 3 | 4 | 12 | High | IT Operations | Mitigate | Document exit strategy and shared-responsibility ownership | 2026-10-10 | Open | 2 | 3 | 6 | Medium
R-006 | GA-017 | Inconsistent incident severity classification | Security incidents may not receive consistent prioritization or escalation. | Incident management | Inconsistent ticket classification | Severity criteria are not consistently recorded | 3 | 4 | 12 | High | SOC / IT Security | Mitigate | Make severity classification mandatory in incident workflow | 2026-09-10 | In Progress | 2 | 3 | 6 | Medium
R-007 | GA-022 | Incomplete PII inventory | Personal information may be processed without complete visibility of ownership and handling requirements. | PII / customer information | Incomplete PII mapping | Several SaaS tools are missing from the PII inventory | 4 | 5 | 20 | Critical | Privacy / Legal | Mitigate | Complete PII inventory and ownership mapping | 2026-09-30 | Open | 3 | 4 | 12 | High
R-008 | GA-023 | No independent security review | Control weaknesses may remain unidentified due to lack of independent challenge. | ISMS / security governance | No independent review | No independent information security review completed in the period | 3 | 5 | 15 | High | CISO / Management | Mitigate | Schedule independent ISMS/security review and track findings | 2026-10-15 | Open | 2 | 4 | 8 | Medium
R-009 | GA-028 | Incomplete contractor endpoint visibility | Unmanaged contractor devices may introduce malware or data leakage risk. | Endpoint devices | Incomplete compliance monitoring | Endpoint compliance reporting does not fully cover contractors | 3 | 5 | 15 | High | IT Operations | Mitigate | Extend endpoint compliance monitoring to contractor devices | 2026-09-30 | Open | 2 | 4 | 8 | Medium
R-010 | GA-034 | Privileged access recertification gap | Excessive privileged access may remain active, increasing compromise impact. | Privileged accounts | Incomplete review | Quarterly privileged access recertification is incomplete | 4 | 5 | 20 | Critical | IT Security | Mitigate | Complete privileged access recertification and exception review | 2026-09-15 | In Progress | 3 | 4 | 12 | High
R-011 | GA-035 | Incomplete MFA coverage | Legacy applications may be accessed with weaker authentication controls. | Legacy applications | MFA not universal | MFA is not yet enabled for all legacy internal applications | 4 | 5 | 20 | Critical | IT Security | Mitigate | Extend MFA to remaining legacy applications | 2026-10-01 | Open | 3 | 4 | 12 | High
R-012 | GA-037 | Overdue vulnerability remediation | Known vulnerabilities may remain exploitable beyond defined remediation expectations. | IT infrastructure | Remediation SLA breach | Some high-severity vulnerabilities exceed remediation SLA | 4 | 5 | 20 | Critical | IT Operations | Mitigate | Escalate overdue high-severity vulnerabilities and track exceptions | 2026-08-31 | In Progress | 3 | 4 | 12 | High
R-013 | GA-040 | Insufficient centralized monitoring | Security events in critical systems may not be detected promptly. | Critical systems | Monitoring coverage gap | Several critical systems lack centralized monitoring and alert escalation | 4 | 5 | 20 | Critical | IT Security | Mitigate | Implement centralized monitoring for critical systems | 2026-11-15 | Open | 3 | 4 | 12 | High

## Remediation_Tracker
Action_ID | Risk_ID | Assessment_ID | Gap | Remediation_Action | Owner | Priority | Start_Date | Target_Date | Status | Completion_Percentage | Evidence_Required | Closure_Notes
ACT-001 | R-001 | GA-004 | Threat intelligence review process is not formalized | Define approved intelligence sources, monthly review cadence and decision log. | IT Security | Medium | 2026-07-10 | 2026-09-30 | Open | 0 | Threat intelligence review log
ACT-002 | R-002 | GA-005 | Asset inventory does not fully cover SaaS/information assets | Complete discovery, assign owners and establish quarterly review. | IT Operations | High | 2026-07-10 | 2026-09-20 | Open | 0 | Updated asset register and review record
ACT-003 | R-003 | GA-007 | Information labeling is inconsistent | Refresh classification guidance and perform sample compliance checks. | Information Security | Medium | 2026-07-10 | 2026-09-25 | Open | 0 | Classification compliance check
ACT-004 | R-004 | GA-012 | Quarterly access recertification is incomplete | Complete certification for all critical applications and document exceptions. | IT Security | High | 2026-07-10 | 2026-09-15 | In Progress | 50 | Signed access certification report
ACT-005 | R-005 | GA-015 | Cloud exit planning is inconsistent | Create exit checklist, data return/deletion requirements and ownership matrix. | IT Operations | Medium | 2026-07-10 | 2026-10-10 | Open | 0 | Approved cloud exit plan
ACT-006 | R-006 | GA-017 | Incident severity is not consistently recorded | Make severity classification mandatory in incident workflow. | SOC / IT Security | Medium | 2026-07-10 | 2026-09-10 | In Progress | 40 | Updated incident workflow and sample tickets
ACT-007 | R-007 | GA-022 | PII inventory is incomplete for some SaaS tools | Complete PII discovery, ownership mapping and processing register updates. | Privacy / Legal | High | 2026-07-10 | 2026-09-30 | Open | 0 | Updated PII inventory
ACT-008 | R-008 | GA-023 | Independent security review has not been performed | Schedule independent review, record findings and assign corrective actions. | CISO / Management | High | 2026-07-10 | 2026-10-15 | Open | 0 | Independent review report
ACT-009 | R-009 | GA-028 | Contractor endpoint compliance visibility is incomplete | Extend endpoint compliance monitoring to contractor devices. | IT Operations | High | 2026-07-10 | 2026-09-30 | Open | 0 | Endpoint compliance report
ACT-010 | R-010 | GA-034 | Privileged access recertification is incomplete | Complete quarterly privileged access certification and exception review. | IT Security | High | 2026-07-10 | 2026-09-15 | In Progress | 50 | Privileged access review report
ACT-011 | R-011 | GA-035 | MFA is not universal for legacy applications | Implement MFA for remaining legacy applications using approved compensating controls where necessary. | IT Security | High | 2026-07-10 | 2026-10-01 | Open | 0 | MFA coverage report
ACT-012 | R-012 | GA-037 | High-severity vulnerability remediation exceeds SLA | Escalate overdue vulnerabilities, assign owners and document approved exceptions. | IT Operations | Critical | 2026-07-10 | 2026-08-31 | In Progress | 60 | Vulnerability remediation report
ACT-013 | R-013 | GA-040 | Centralized monitoring is missing for several critical systems | Implement monitoring, alert routing and escalation for critical systems. | IT Security | Critical | 2026-07-10 | 2026-11-15 | Open | 0 | Monitoring coverage report and alert test evidence

## Evidence_Index
Evidence_ID | Evidence_Type | Related_Control | Related_Assessment | Description | Owner | Review_Status | Notes
EV-001 | Policy | A.5.1 | GA-001 | Approved information security policy, version history and review record. | Information Security | Available | Simulated evidence reference
EV-002 | RACI | A.5.2 | GA-002 | Information security responsibilities and RACI matrix. | Information Security | Available | Simulated evidence reference
EV-003 | Management Record | A.5.4 | GA-003 | Quarterly security governance meeting minutes. | Management | Available | Simulated evidence reference
EV-004 | Threat Intelligence Record | A.5.7 | GA-004 | Threat source review record and intelligence log. | IT Security | Partial | Formal recurring review not yet established
EV-005 | Asset Register | A.5.9 | GA-005 | Hardware and application asset register. | IT Operations | Partial | SaaS/information ownership incomplete
EV-006 | Classification Policy | A.5.12 | GA-007 | Information classification scheme and samples. | Information Security | Partial | Labeling consistency gap
EV-007 | Access Review | A.5.18 | GA-012 | Quarterly access recertification report. | IT Security | Partial | Coverage incomplete
EV-008 | Supplier Assessment | A.5.19 | GA-013 | Supplier security due diligence record. | Procurement / Security | Partial | Coverage varies by supplier risk
EV-009 | Cloud Assessment | A.5.23 | GA-015 | Cloud provider security assessment. | IT Operations | Partial | Exit planning gap
EV-010 | Incident Plan | A.5.24 | GA-016 | Incident response plan and escalation matrix. | IT Security | Available | Simulated evidence reference
EV-011 | PII Inventory | A.5.34 | GA-022 | PII processing inventory. | Privacy / Legal | Partial | SaaS coverage incomplete
EV-012 | Independent Review | A.5.35 | GA-023 | Independent security review report. | Management | Missing | Not yet performed
EV-013 | Training Report | A.6.3 | GA-026 | Security awareness completion report. | HR | Available | 96% completion
EV-014 | Physical Access Log | A.7.2 | GA-030 | Badge and visitor records. | Facilities | Available | Sampled records
EV-015 | Privileged Access Review | A.8.2 | GA-034 | Privileged account inventory and certification. | IT Security | Partial | Quarterly recertification incomplete
EV-016 | MFA Report | A.8.5 | GA-035 | MFA coverage report. | IT Security | Partial | Legacy applications excluded
EV-017 | Vulnerability Report | A.8.8 | GA-037 | Monthly vulnerability scan and remediation report. | IT Operations | Partial | Some high findings overdue
EV-018 | Backup Report | A.8.13 | GA-038 | Backup and restore test report. | IT Operations | Available | Simulated evidence reference
EV-019 | Logging Standard | A.8.15 | GA-039 | Central logging standard and retention settings. | IT Security | Partial | Legacy retention inconsistent
EV-020 | Monitoring Assessment | A.8.16 | GA-040 | Monitoring coverage assessment. | IT Security | Missing | Centralized monitoring gap

## Lookup_Lists
Assessment_Status | Evidence_Available | Priority | Risk_Treatment | Risk_Status | Remediation_Status | Likelihood | Impact | Risk_Band | Score | Risk Level | Response
Implemented | Yes | Low | Mitigate | Open | Open | 1 | 1 | Low | 1–4 | Low | Routine monitoring
Partially Implemented | Partial | Medium | Accept | In Progress | In Progress | 2 | 2 | Medium | 5–9 | Medium | Planned treatment
Not Implemented | No | High | Transfer | Accepted | Blocked | 3 | 3 | High | 10–16 | High | Priority treatment
Not Applicable |  | Critical | Avoid | Closed | Completed | 4 | 4 | Critical | 17–25 | Critical | Urgent management attention
[5 empty] | Accepted | 5 | 5

## Data_Dictionary
Sheet | Field | Meaning | Expected Values / Format
Control_Master | Control_ID | Unique identifier for selected Annex A control. | A.x.x
Control_Master | Control_Category | One of the four Annex A theme groups used in this project. | Organizational / People / Physical / Technological
Gap_Assessment | Assessment_ID | Unique identifier for an assessment record. | GA-###
Gap_Assessment | Status | Current implementation status based on simulated evidence. | Implemented / Partially Implemented / Not Implemented / Not Applicable
Gap_Assessment | Maturity | Simple portfolio maturity label derived from status. | Defined / Operating; Defined / Partially Operating; Not Established
Gap_Assessment | Evidence_Available | Whether evidence supporting the assessment was available. | Yes / Partial / No
Gap_Assessment | Priority | Remediation priority assigned to the gap. | Low / Medium / High / Critical
Risk_Register | Likelihood | Estimated probability rating for the risk. | 1–5
Risk_Register | Impact | Estimated business impact rating for the risk. | 1–5
Risk_Register | Inherent_Risk_Score | Risk before additional treatment. | Likelihood × Impact
Risk_Register | Residual_Risk_Score | Estimated risk after planned/existing treatment. | Residual Likelihood × Residual Impact
Risk_Register | Risk_Level | Risk band derived from score. | 1–4 Low; 5–9 Medium; 10–16 High; 17–25 Critical
Remediation_Tracker | Completion_Percentage | Progress against remediation action. | 0–100